## Project
[6 empty] | Aug |  |  |  | Sep |  |  |  | Oct |  |  |  | Nov |  |  |  | Dec |  |  |  | Jan
Sl No | Catagory | Sub-Catagory | Responsible | Task | Sub-task | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21
1 | Project Mgnt |  | Raju | Get latest Robol files together
2 | RnD | Rora |  | Wheel alignment solution | Try method-1
3 | RnD | Rora |  | Wheel alignment solution | Try method-2
4 | RnD | Rora |  | Wheel alignment solution | Try method-3
5 | RnD | Rora |  | Wheel alignment solution | Try method-4
6 | Dev | Skillset | Intern-1-Hardware | Build expertise on PCB making using EAGLE Free version | 2 Weeks complete tutorials and simple circuits
7 | Dev | Rora | Intern-2 | Final Block diagram for Rora
8 | Dev | Rora | Intern-2 | Dimension of the board
9 | Dev | Rora | Intern-2 | Finalise modules and sensors to be used in Rora
10 | Dev | Rora | Intern-2 | Finalise Mechanical parts to be integrated with PCB
11 | Dev | Rora | Intern-2 | Design schematic
12 | Dev | Rora | Intern-2 | Test SChematic with General purpose PCB
13 | Dev | Rora | Intern-2 | PCB Design
14 | Dev | Rora | Intern-2 | Fabricate PCB
15 | Dev | Rora | Intern-2 | Procure components
16 | Dev | Rora | Intern-2 | Assemble PCB
17 | Dev | Rora | Intern-2 | Test and finalise the PCB
18 | Dev | Slate | Intern-3-Mech | Workout new miniature design for Slate
19 | Dev | Slate | Intern-4 | Finalize code on Slate all modules
20 | Dev | Slate | Intern-4 | Error catagories
21 | Dev | Slate | Intern-4 | Optimised scanning method
22 | Dev | Slate | Intern-4 | Final number of coins
23 | Dev | Slate | Intern-4 | Method to have colored coins
24 | Dev | Slate | Intern-4 | Design schematic
25 | Dev | Slate | Intern-4 | Test SChematic with General purpose PCB
26 | Dev | Slate | Intern-4 | PCB Design
27 | Dev | Slate | Intern-4 | Fabricate PCB
28 | Dev | Slate | Intern-4 | Procure components
29 | Dev | Slate | Intern-4 | Assemble PCB
30 | Dev | Slate | Intern-4 | Test and finalise the PCB
31 |  | Rora |  | Understand existing code modules
32 |  | Rora |  | Make software architecture
33 |  | Rora |  | Update pending modules in Rora
34 |  | Slate |  | Understand existing code modules
35 |  | Slate |  | Make software architecture
36 |  | Slate |  | Update pending modules in Rora

## Groups
Sl no | Name | Passionate about
1 | Anush | Mechanical and Coding | M S Ramaiah - Btech Passed Out
2 | Akshay | Alrounder - Graphics designer | 7th Sem
3 | Abhishek | Hardware and wants to Learn Coding
4 | Mano Selvamani | Hardware, Electrical, Mechanical, Automation | PG Diploma
5 | Ayesha Firdous | Hardware | Mtech JSS
6 | Ashwini | Coding, Coding, Coding | Mtech JSS
| Teams |  | Partners | Followers
Mech | Mechanical | Anush | Abhishek | Ayesha
Elect | Electrical and Automation | Mano Selvamani | Abhishek | Ayesha
Hware | Hardware - PCB Design | Ayesha Firdous | Mano Selvamani | Abhishek, Ashwini
Coding | Programming | Ashwini | Anush | Abhishek, Mano Selvamani
Content | Content Writing | Hari Priya
| Over all Team headed by | Khushroo